## Sheet1
Risk | Category | Probability | Impact | Risk Exposure | Pointer to RMMM
Complex System Functionality | Technology | Likely (80%) | 2 | 20200 | Mitigation: - Have specific training for resources in skills they are lacking of - Backups of resources and provision of laptops - Have Company Business Structure training for the team Monitoring: - Ensure System Functionality is well-documented - Ensure System is checked daily for bugs and update. Have UPS in case of power outage - Ensure changes are documented and cascaded to team members Management: - Have Business Continuity Plan - Have rollback procedures
Poor knowledge of project resources | Business | Occasional (60%) | 3 | 9000
Availability of resources | Business | Unlikely (0%) | 1 | 0
System downtime due to power outage/bugs | Technology | Unlikely (0%) | 1 | 0
Extensive changes required to existing infrastructure | Technology | Seldom (25%) | 2 | 1125
Limited business knowledge of the project team | Business | Likely (80%) | 4 | 14400